## Slide 1
<number>
Synthesis HoMs reports on Joint Programming
26 April 2013
Technical Seminar on EU Programming and Joint Programming
DEVCO/A5 Aid and Development Effectiveness and Financing
EEAS/VI.B.2 Development Cooperation Coordination Division
Notes: DEVCO- Bernard San Emeterio
<number>
<number>

## Slide 2
JP HoMs reports: process & quality
Majority of reports on time
Reports seem to be backed by serious debate and consultation
Overall good quality addressing key issues
Showing good understanding of issue of JP (thanks to clear instructions from HQs)
Notes: DEVCO- Bernard San Emeterio
<number>

## Slide 3
JP HoMs reports: fact & figures
2 countries where JP already started before and no HoMs reports required (Haiti and South Sudan)
12 HoMs report received in 2012 (for Mali update requested)
Following EU DGs meeting HoMs reports requested from 41 other countries by EEAS/DEVCO note Dec 2012
So far 36 HoMs reports received in 2013 and shared with MS
5 reports still pending: Armenia, Jordan, Libya and Somalia (only notes from DEL); Timor Leste
Notes: DEVCO- Bernard San Emeterio
<number>

## Slide 4: State of Play (of 55 countries in total)
  40 Positive: 30 new countries! + 10 countries agreed in 2012 (incl. Mali)
  13 To be further reviewed or to be received: 8 to be reviewed: Algeria, El Salvador, oPt, Vietnam, Zimbabwe, Afghanistan, Moldova, Tunisia 5 reports to be received
  2 No's Zambia (revisit at end of election cycle), Ukraine

## Slide 5: Examples of Progress so far (1)
  Bangladesh: joint political analysis started and shared EU vision process
  Ethiopia: EU Joint Cooperation Strategy signed end of January 2013; Roadmap with next steps agreed
  Ghana: JP builds on donor wide Country Compact; joint Multi-annual Indicative Programme
  Guatemala and Laos: JP document submitted to HQs in December 2012
  Mali: ministers reconfirmed commitment on 26 Feb 2013; two phase approach; updated HoMs report due
  Rwanda: JP documents will be submitted end of May 2013

## Slide 6: Examples of Progress so far (2)
  Haiti, South Sudan: JP on-going, moving to second generation of JP
  Senegal, Namibia: joint analysis done and full JP in preparation
  Cote d'Ivoire, Togo, Burundi, Chad, Bolivia: joint analysis done
  Cambodia, Paraguay: move towards JP after this year's elections
  Egypt, Kenya, Liberia: joint response in 2013

## Slide 7: 'Country type' breakdown
  MICs: 11
  LDC/LICs: 17
  Fragile states: 12 (based on World Bank list + Mali)

## Slide 8: Regional breakdown
  West-Africa: 11
  Central Africa: 3
  East Africa: 6
  Southern Africa: 3
  Asia: 7
  Latin America & Caribbean: 6
  Neighbourhood: 4

## Slide 9: Synchronisation
  In several countries synchronisation will take place
  Still remains challenge in others: ex. Uganda
Uganda | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
NDP |  |  |  |  |  |  | 
EU |  |  |  |  |  |  | 
BE |  |  |  |  |  | ? | 
DE |  |  |  |  |  | ? | 
DK |  |  |  |  |  | ? | ?
IR |  |  |  |  | ? |  | 
IT |  |  |  | ? | ? |  | 
NL |  |  |  |  |  |  | 
SE |  |  |  | ? | ? |  | 
UK |  |  |  |  |  |  | 

## Slide 10: Windows for synchronisation/JP per year
2013/2014 | 2015 | 2016 | 2017 | 2018 | To be confirmed
Bangladesh | Comoros | Afghanistan | Bolivia phase 2 | Cambodia phase 2 | Algeria
Bolivia |  | Bangladesh phase 2 | Georgia | Honduras | Mali phase 2
Burma/Myanmar |  | Benin | Ghana phase 2 | Kenya phase 2 | Moldova
Burundi |  | Burkina Faso | Guatemala phase 2 | Liberia phase 2 | oPt
Cambodia |  | Burma/ Myanmar phase 2 | Haiti phase 3 | Nicaragua | Timor Leste
Chad |  | Burundi phase 2 | Nepal | Paraguay phase 2 | 
Côte d'Ivoire |  | Chad phase 2 | Philippines | Rwanda phase 2 | 
Egypt |  | Côte d'Ivoire phase 2 | Senegal phase 2 |  | 
Ethiopia |  | Egypt phase 2 | Sierra Leone |  | 
Ghana |  | El Salvador | South Sudan phase 3 |  | 
Guatemala |  | Ethiopia phase 2 | Togo phase 2 |  | 
Haiti phase 2 |  | Laos phase 2 |  |  | 
Kenya |  | Malawi |  |  | 
Laos |  | Mauritania |  |  | 
Liberia |  | Morocco |  |  | 
Mali |  | Mozambique |  |  | 
Namibia |  | Niger |  |  | 
Paraguay |  | Pakistan |  |  | 
Rwanda |  | Tanzania |  |  | 
Senegal |  | Tunisia |  |  | 
South Sudan phase 2 |  | Uganda |  |  | 
Togo |  | Vietnam |  |  | 
 |  | Yemen |  |  | 
 |  | Zimbabwe |  |  | 

## Slide 11: Stakeholders
  In most JP countries all MS join JP
  JP seen as more challenging in donor-crowded countries, but also of higher value
  Non-EU donors (Norway, Switzerland; Canada, United States, Japan interested) participate in a number of countries.
  Partner countries: generally supportive, to be involved from the beginning as far as possible

## Slide 12: Enabling factors for JP
EU accountable on its JP commitment to international community (Busan deliverable)
Lisbon treaty: calls for complementarity and coordination; mandate for EU Delegations to coordinate EU development cooperation
Agenda for Change: EU common development policy
New global realities (power shift and multiple crises) push EU to work together
Conviction within EU that JP will lead to more efficiency, higher impact, visibility and effectiveness
Conceptual approach now generally well understood
Investment of EU and MS in operational follow-up at HQ and field level is absolutely key; including better and continuous communication;
Headquarters instructions from HQs to HoMs/HoCs sometimes need to be improved

## Slide 13: Discussion:
Lessons from field missions and synthesis of HoMs' reports:
Do you agree with the assessments?
Do responses fulfil your expectations?
Do you agree that this will be the final list of JP countries?