## Slide 1: Supporting change through Capacity Development
Module 8:
Appropriate Programme
Implementation Arrangements

## Slide 2: This Module
  Explains why the design of programme implementation arrangements is important for capacity development
  Provides an overview of key considerations for designing effective implementation arrangements

## Slide 3: CD Quality grid requirements: 5. Appropriate PIA
5.1 Briefly describe the Project Implementation Arrangement. Will country partners lead and manage the programme? Is primary accountability of the programme appointed to domestic stakeholders?
5.2 Will civil servants working in the programme receive topping-up (salary supplements, special allowances etc.) funded by the EU? Are they linked to clear performance targets? If these incentives are not following government regulations, which steps will be taken to align them, diminish any negative distortion and/or abandon the use of donor-funded topping-up?

## Slide 4: … continued
5.3. Given the nature of the programme and of the expected results, explain its level of integration in the broader structure or its level of autonomy
5.4 Are the EU’s and/or other donors’ role in the governance of the programme limited to oversight functions?

## Slide 5: Orientation
Avoid Parallel Project Implementation Units, unless perfectly justified, and desired by domestic stakeholders
Primary accountability is to domestic stakeholders
How well is the support integrated into the country institutional set-up ?
Can the implementation mechanisms be closer to country systems ? Procurement, accountability mechanisms (Budget, Parliament, Court of Auditors)
Issue of salary top-ups and related incentives has been addressed
EU/donor role is limited to oversight

## Slide 6: Importance of proper arrangements
  Poorly designed arrangements can undermine the integrity of a CD intervention
  Fragmented management and governance
  Draw on scarce resources
  Unsustainable and can create perverse incentives
  Well conceived PIAs can make an important contribution to sustainable capacity development
  Tackle CD as a key design consideration
  Make ownership operational in day-to-day working relations

## Slide 7: PIA characteristics
<number>
Partner-owned and partner managed
Designed/ decided by the partner with donor input
Embedded in the local institutional context
Balancing programme autonomy vs. integration. Depends on type of result envisaged:
  Extent to which results can be achieved without inputs/ resources of other organisations within public sector
  Extent to which CD and change is key objective

## Slide 8: Designing PIAs: 5 key parameters
<number>
1. Governance and accountability
  Who should oversee and govern programme implementation?
  Who should the programme be accountable to in the country system?
  Take care to avoid duplication
2. Management set-up
  Who will perform daily programme management functions?
  With what authority over resource management functions?
  A part-time or full time function?

## Slide 9
<number>
3. Logistical autonomy & embeddedness
  Does the programme require own vehicles, office equipment, ancillary staff, or can it share resources with others?
  Legitimacy, sustainability, efficiency
4. Relations between TC experts, partners and EC
  If contracted by the EC (or another donor), who are the experts taking instructions from and to whom are they accountable?
  Trust, accountability and confidentiality
5. EC’s and other donors’ roles
  Should donors play a role at all in the PIA – and if so, which role?
  Policy dialogue, negotiating results framework, M&E

## Slide 10: And what about TA?
CD support
CD processes
Recurrent inputs
Capacity
Outputs
Outcomes
Wider impact
Internal resour-ces
TC support
Recurrent inputs
Capacity
Outputs
Outcomes
Wider impact
1.
2.

## Slide 11: Balancing “Doing” and “Facilitating”
Combining service delivery and CD support may appear ideal ….. BUT
The risk is that strong drivers (disbursement and visible short-term results which politicians on both sides) will overwhelm CD objectives unless there is a strong, articulated demand for it matching the demand for implementation.
In situations where “doing” takes over, it may end up reducing existing capacity:
  de-motivating lower remunerated staff
  undermining domestic systems and accountability
  poaching

## Slide 12
ATTENTION FOR PARTNER GROWTH
ATTENTION FOR PROGRAMME RESULTS
counseler
coach
partner
philosopher
facilitator
technical adviser
teacher
model
expert
Agree on the TA’s role

## Slide 13: Partner Management of TA
  TORs developed with and approved by the partner agency
  Active partner role in recruitment/procurement process even if not contracting: prepare thoroughly
  Partner agency lead responsibility for / active engagement in supervision (giving instructions) and reporting

## Slide 14: Balance the three-way relationship
Doer?
Middleman?
Mediator?
Facilitator?
Controller? Spy?
TA
Donor
Customer?
Client?
Beneficiary
Partner?
Stakeholder?
Employer?
Local Organisations
Employer?
Stakeholder?
Customer?
Partner?
Benefactor?