## Slide 1: RAPID ASSESSMENT OF CAPACITY DEVELOPMENT (RAC)
A non-invasive approach to assess Capacity Development outcomes
What is it? How can it help?

## Slide 2
To present to EU staff in Headquarters and Delegations the methodological approach for RAPID ASSESSMENT OF CAPACITY DEVELOPMENT (RAC).
This presentation should allow EU staff to understand the main features of the RAC.
The RAC can be carried out either internally (by EU staff), or externally (by consultants), or by a mixed team (e.g. EU staff with the support of a local consultant).
The RAC is a quick exercise that can be carried out within a period of up to two months.
Purpose of this material
<number>

## Slide 3
Capacity development is a strategic objective of development cooperation which has a significant impact on aid effectiveness.
Why a RAC?
<number>
The RAC focuses on institutional capacity development processes, and provides answers to questions such as: How did the people and their relations in the targeted institution/s evolve? Did the institution gain in independence, initiative, resilience, etc? What where the main factors contributing to this?
Responding to such questions requires a specific approach.
Notes: The RAC is based on a thorough evaluation methodology, according to the EU evaluation guidelines. It shares many features with similar methodologies recently elaborated and tested by different international agencies, namely the United Nations Development Programme (UNDP), the World Bank Institute (WBI), and particularly the 5Cs (five capabilities) methodology developed by the ECDPM (European Centre for Development Policy Management).
<number>

## Slide 4: What is the purpose of the RAC?
  The purpose is to assess the impact of an intervention in terms of capacity development at institutional level.
The RAC builds on current EU Technical Cooperation reform (i.e. Backbone strategy) and the Aid Effectiveness agenda.
<number>
It is as if, before setting off on a long journey, we would open the bonnet of our car, to check how the engine and the other mechanical parts are working and whether they need any work on maintenance to guarantee that the car safely arrives at our destination.
Notes: “Intervention” is used here, and from now on, in a broad sense (it can be a single support programme, a set of programmes in a given sector, a set of programmes in a given country and in different sectors)
<number>

## Slide 5
<number>
Key definitions
Capacity:
the ability of people, organisations and society as a whole to manage their affairs successfully. (OECD definition)
Capacity development:
the process by which individuals, organisations, institutions and countries develop, enhance and organise their systems, resources and knowledge; all reflected in their abilities, individually and collectively, to perform functions, solve problems and achieve objectives. (OECD definition)
Capacity output :
Actual changes in individual and organisational capabilities (e.g. staff competencies, procedures and organisational setup)
Capacity outcome:
Overall capacity that is necessary for the accomplishment of the institutions’ mission, beyond the duration of any external aid intervention.
Notes: <number>

## Slide 6: Capacity development as an institutional learning process
With a past, a present and a future …
… to which the development intervention may contribute by strengthening and valorizing acquired capacities and/or by introducing new capacities.
This temporal variable is crucial to the RAC since capacity development is part of a complex process with different stakeholders and interactions at various levels.
<number>
Notes: Although the RAC focuses on the impact of an intervention in terms of capacity development, this intervention never takes place in a situation of isolation, like in a laboratory. Therefore, the contribution of the development intervention to capacity development, is assessed as part of wider institutional learning process with a past, a present and a future.
<number>

## Slide 7: The features of the RAC
    It meant to be used in the context of an evaluation of a project/ budget support programme, provided that the respective intervention aims to develop capacities at institutional level (either directly or through a significant CD component);
    It is light in terms of time and € (ToR template for the RAC are available upon request). Indicative number of days needed:
      Standard RAC: 1 international expert (~21 days) & 1 national expert (~22 days); total duration of up to 2 months;
    It provides immediate feedback/information that can lead to a greater awareness on the learning processes.
    It can be applied:
      ex-ante (see notes below): to establish a baseline of capacities in the targeted institution and to support the design of a CD intervention.
      during the intervention (for potential adjustments).
      ex-post (at the end of an intervention cycle and potentially for the definition of a new one).
<number>
Notes: If the RAC is applied ex-ante, the methodology described here will need to be adapted. The objective will no longer be to assess the contribution of a specific intervention to capacity development. The focus will rather be to establish a baseline and thereby identify the key capacity constraints that a CD intervention should aim to address.
The RAC has already been tested ex-post, in the framework of a budget support intervention, of a sector approach and of a programme.
<number>

## Slide 8: The features of the RAC
    It is largely based on a participatory approach, allowing the stakeholders of the beneficiary institution to play an important role in the exercise. The evaluator and the stakeholders thus work for a common objective.
    It can be applied to different aid modalities (project/programme approach, budget support);
    It should help improve the design and management of development actions, through a stronger consideration of the CD processes involved.
<number>
Notes: <number>

## Slide 9: RAPID ASSESSMENT OF CAPACITY DEVELOPMENT (RAC)
Introduction to the Intervention Logic and the 4 Steps of the RAC

## Slide 10: Integrating Capacity Development in the Intervention Logic of a standard development intervention
<number>
See explanatory notes below!
Notes: The blue part represents the standard chain of results of a development action. The yellow part represents the Capacity Development (CD) chain which interacts with the standard chain of results at all levels. This interaction is influenced by a number of factors (enabling factors). The RAC is focusing on better understanding the yellow chain.
The programme inputs may generate changes in staff skills, procedures and organisation of responsibilities (CD outputs), which in turn may or may not result into improvements in the core capabilities of an institution (CD outcomes).
<number>

## Slide 11
<number>
Adaptation
Initiative
Achieve
Results
Coherence
Institutional
networking
Capacity outcomes
Enabling Factors/
Context
Opportunity Framework
Fits to context
Capacity outputs
New staff competencies created
New procedures established
New organisational and functional set up
Capacity inputs
Funds
Training
Policy dialogue
Capacity
Inputs
Step 1
Step 2
Step 3
Quality Criteria
Demand and ownership
Harmonised support
Link to results and expected outcomes
Implementation arrangements
Step 4
See explanatory notes below!
Notes: The diagram above depicts the generic Intervention Logic on which the RAC is based (Capacity Development chain in the previous slide) and the 4 steps of the methodological approach.
This intervention logic is to be used as a capacity development roadmap which must be adapted to the specific issue at hand. The RAC is carried out in 4 steps as follows:
Step 1 Assessment of the enabling factors. This includes an analysis of the context (opportunity framework) in which the intervention was/is implemented in order to identify potential external factors that may facilitate/ hinder the capacity development process and assess the extent to which the intervention takes those factors into account; This step also includes an assessment of the extent to which the capacity inputs fulfil the quality criteria set out in the EU Backbone Strategy.
Step 2 – Assessment of the capacity outputs. This includes an analysis of the extent to which there have been changes in the individual skills, procedures or organisational set up in the supported institution. The evaluators then asses to what extent the capacity inputs of the programme have contributed to those changes.
Step 3 – Assessment of the capacity outcomes. This includes an analysis on the extent to which there have been changes in the key capabilities of an institution in areas such as: 1) production of relevant initiatives 2) effective networking with relevant institutions; 3) constant adaptation to changes in the context; 4) achievement of the objectives stated in the institution's plan; 5) coherence between the strategic and operational levels of the institution. The evaluators than assess the extent to which such changes can be related to the changes in the capacity outputs.
Step 4 – Summary of the analysis. In this step the links between the inputs of the CD programme, capacity outputs and capacity outcomes are further verified in order to complete the assessment.
<number>

## Slide 12: A 4-steps approach
<number>
Notes: <number>

## Slide 13: Assessment of the Opportunity framework
Assessment of the influence of the political/strategic framework and of the EU partnership relations with the country on the Capacity Development (CD) process in the institution concerned.
This leads to the identification of:
  Facilitating factors that positively influence the capacity development process and therefore also the development intervention.
  Factors that tend to hinder or limit the effectiveness of the capacity development process.
This assessment should determine the role played by the intervention within the CD process (catalyst of initiatives or rupture with respect to previous efforts).
<number>
Notes: <number>

## Slide 14
This should tell if the intervention (including the quality of its design, and the delivery methods) fits a set of conditions (EuropeAid QC) which are conducive to capacity development. These are:
Is ideally driven by the country, within a dialogue framework with the donor(s)
Fits to the context
Responds to a demand and political commitment
Is linked to specific CD effects
Sets peer-to-peer implementation arrangements
Assessment of the Quality criteria
4
3
1
5
QC
2
<number>
Notes: <number>

## Slide 15: A 4-steps approach
<number>
Notes: <number>

## Slide 16: Assessment of capacity outputs
Any significant changes that have taken place in the targeted institution/s (in terms of staff skills, procedures and organisation of responsibilities) must be identified. We then need to assess whether the capacity inputs of the programme have contributed to these changes.
Examples of CD outputs:
Systematization of information;
Better time management;
Specific staff competences acquired (e.g. project management)
These changes may (or may not) have been translated into a strengthening of the institution's overall capabilities (CD outcomes).
”
“
<number>
Notes: The changes in organisational set-up, possibly promoted or facilitated by the programme, range from the creation of new units (e.g. monitoring and evaluation), to the reduction of organisational overlapping, the adoption of a decentralized structure, and so on.
<number>

## Slide 17: A 4-steps approach
<number>
Notes: <number>

## Slide 18: Assessment of capacity outcomes
Any significant changes in the core capabilities of an institution (capacity outcomes) must be identified. We then need to assess whether these changes have been determined by the changes at capacity output level (staff skills, procedures, organisation of responsibilities).
The capacity outcomes are:
<number>
Adaptation
Initiative
Achieve Results
Institutional networking
4
3
2
1
5
Coherence
(Link the strategic and operational levels)
Notes: Capacity outcomes are the sequential effect of the CD outputs. Outcomes determine the effectiveness of the outputs and their analysis allows understanding the possible problems that need to be solved in the production of CD outputs.
These capacities are necessary for the accomplishment of the institutions’ mission, beyond the duration of any external aid intervention, and are therefore the basis for the continuity of the institution.
<number>

## Slide 19
Initiative
Capacity to generate initiatives (plans, laws, operations, etc.) that reflect the institution's needs and mission; and capacity to mobilize resources to execute them.
Achieve Results
Capacity to reach (in a sustainable way) the development results stated in national and sector policies and "departmental" plans.
Examples:
Increased autonomy in reporting, analysis & management of indicators
Capacity for seeking diversified funding sources
Increased sector leadership and positioning
Capacity to outperform the proposed targets
Assessment of capacity outcomes
“
”
<number>

## Slide 20
Institutional networking
Capacity to work in a coordinated and efficient manner as part of a larger network of interested stakeholders. This also involves knowledge sharing within a network.
Adaptation
Capacity to constantly adapt in response to changing external environments and conditions.
Examples:
Better relations and networking links with other key institutions at national or international level
Ability to better learn from experience
Capacity to identify changes in the context and correct/reorient the allocation of resources accordingly
Assessment of capacity outcomes
“
”
<number>

## Slide 21
Coherence (link the strategic and operational levels)
Capacity to put in place policy and management frameworks that build upon one another and provide evidence of a clear chain of results from the strategic to the operational levels.
Examples:
Improved internal coordination and management of human resources
Improved adaptation of the management structure to the institution's mission and objectives
Assessment of capacity outcomes
“
”
<number>

## Slide 22: A 4-steps approach
<number>
Notes: <number>

## Slide 23: Summary (and verification) of the analysis
In this step the links established in the previous 3 steps are summarised and further verified.
The relationships between the enabling factors, capacity inputs, capacity outputs and capacity outcomes, are summarised and the contribution story is developed.
Examples:
“
Enabling factors | Capacity inputs | Capacity output | Capacity outcome
- Political commitment | Training | Project management competencies strengthened | Increased autonomy in reporting, analysis & management of indicators
Harmonized support | Technical Advice | Systematization of information | Ability to better learn from experience
Internally driven process | Technical Advice | Reorganisation of the institution | Improved adaptation of the management structure to the institution's mission and objectives
”
<number>

## Slide 24: RAPID ASSESSMENT OF CAPACITY DEVELOPMENT (RAC)
How to carry out its 4 steps:
Initial questions to be asked at the beginning of each step
&
Data collection tools

## Slide 25: Initial questions to be asked at the beginning of each step
… to focus data collection on a limited number of key issues.
The questions are not static; they are further developed based on the information gathered.
<number>
Notes: It is highly important to focus the attention to the key information needs. This avoids spending too much time on issues which are not relevant to the objective pursued.
The question is the light that guides the data collection process.
It is key to use a simple language (avoid technicalities). Important to speak in terms of “learning”, (avoid the use of words such as “output”, “outcome”, etc.) It is the role of the evaluation team to determine whether a specific learning, a specific capacity, can be considered a capacity-output or a capacity-outcome (the definitions given in this material, and the fact that there is a temporal sequence between them, should facilitate this task).
<number>

## Slide 26: Data collection tools used in each Step
STANDARD RAC QUESTIONNAIRE
INDIVIDUAL AND COLLECTIVE INTERVIEWS
CO-COACHING
(REFER TO SLIDE 32)
WORKSHOP
SUPPORT INTERVENTION DOCUMENTS
<number>
Notes: <number>

## Slide 27: A 4-steps approach
<number>
Notes: <number>

## Slide 28: Assessment of the enabling factors: Questions
Opportunity framework: - What are the political, institutional and sectoral factors that have facilitated or hindered the capacity development process in the institution?
- Have there been any changes in these factors over time? If yes, did this have an influence on the effectiveness of the intervention?
Quality Criteria:
- Have the capacity inputs been delivered as part of a demand driven process to which the beneficiary institution is fully committed?
- Have the capacity inputs been well coordinated and harmonised with other CD efforts that have taken place in the institution?
- Have the delivery modalities been appropriately chosen?
<number>

## Slide 29: Assessment of the enabling factors – tools to be used
The assessment will be primarily based on individual and collective interviews with:
1) colleagues in the EUD;
2)TA team;
3) staff of the beneficiary institution who have participated in the intervention's activities;
4) other actors who had an indirect interaction with the intervention.
<number>

## Slide 30: A 4-steps approach
<number>
Notes: <number>

## Slide 31: Assessment of capacity outputs
<number>
The first question is:
During the last X years, has the institution shown any significant change in terms of staff competences, procedures and organisation of responsibilities?
The second question is:
Do you think any of these changes have been influenced by the CD inputs (support programme)? If yes, which changes? Why do you think this is the case?

## Slide 32
Tools used:
    RAC questionnaire, which needs to be adapted to the context of the institution analysed.
    This questionnaire is administered through individual and collective interviews with key stakeholders
    Co-coaching (see notes below). The purpose of co-coaching is to encourage beneficiaries to assess by themselves the value of different CD actions (including the value of the inputs of the programme assessed) .
    Workshop. The purpose of the workshop is to further verify and cross-check the findings resulting from the interviews and co-coaching sessions.
Assessment of capacity outputs
<number>
Notes: To be able to apply co-coaching the beneficiaries have to be grouped. The use of this tool is to be considered on a case by case basis depending on:
willingness and interest of the beneficiaries to participate in such exercise;
possibility of grouping beneficiaries.
The co-couching needs to be done after an individual interview with the hierarchic person in charge of the relevant institution. It is important to agree with him the terms of the exercise. A minimum number of 4 people is required.
The co-coaching session is carried out as follows:
  Exercise: each participant is given a sheet of paper listing several learning sources (CD actions) identified during the interviews. This list includes the intervention assessed. They are asked to give weights reflecting the importance of each learning source.
  Work in couple (A and B). A and B exchange their respective sheets of paper of the previous exercise. A asks B about the reasoning behind his percentage distribution, asking for concrete examples and he writes them in B’s sheet, focusing on the effects of the intervention assessed. After this 5 minute exercise, A says to B, with concrete examples, what he (A) has observed in B in terms of learning thanks to the interaction with the intervention and that was not included in B’s sheet. They discuss and if B agrees with the example provided by A, A writes it in B’s sheet. The exercise is repeated changing the roles.
  Work group. Each participant briefs on what happened in the previous exercise and mentions what he considers to be the most important learning acquired in the interaction with the intervention.
<number>

## Slide 33: A 4-steps approach
<number>
Notes: <number>

## Slide 34: Assessment of capacity outcomes
First question is:
Can you mention any important things that the institution couldn't do X years ago, and it is now in a position to do? Specifically, is the institution better capable of:
- producing relevant initiatives (plans, laws, operations)?
- achieving performance in terms of development results?
- being recognised and trusted by stakeholders and able to create good relationships with them?
- learning form experience and adapting to changes in the context?
- adapting the management structure to the institution's mission?
The second question is:
Can you cite the key factors that have contributed to the identified changes?
<number>
Notes: The first question aims to identify changes in the core capabilities of an institution. The specific sub questions need to be adapted to the context of the institution. This is done during the preliminary meetings.
For the second question the interviewer can facilitate the reply by citing changes already identified at capacity output level (changes in staff competences, procedures, or redistribution of responsibilities).
<number>

## Slide 35: Assessment of capacity outcomes
As for the assessment of the capacity outputs, the following tools are used :
    RAC questionnaire, which needs to be adapted to the context of the institution analysed.
    This questionnaire is administered through individual and collective interviews with key stakeholders
    Co-coaching (see notes on slide 32).
    Workshop. The purpose of the workshop is to further verify and cross-check the findings resulting from the interviews and co-coaching sessions.
<number>

## Slide 36: A 4-steps approach
<number>
Notes: <number>

## Slide 37: Summary (and verification) of the analysis
This step requires the organisation of a workshop with all key stakeholders. The purpose is to present the preliminary findings of the RAC on the relationships between: a) enabling factors and CD inputs (step 1); b) CD inputs and CD outputs (step 2) and c) CD outputs and CD outcomes (step 3).
Example:
<number>
“
Enabling factors | Capacity inputs | Capacity output | Capacity outcome
- Political commitment | Training | Project management competencies strengthened | Increased autonomy in reporting, analysis & management of indicators
Harmonized support | Technical Advice | Systematization of information | Ability to better learn from experience
Internally driven process | Technical Advice | Reorganisation of the institution | Improved adaptation of the management structure to the institution's mission and objectives
”

## Slide 38: Synthesis of the RAC
  The evaluation team finally elaborates the RAC note, which presents the findings of the analysis along the 4 steps of the RAC, summarises the main conclusions and provides the contribution story, on the extent to which the CD inputs have resulted in CD outputs which in turn were translated into CD outcomes. The note also presents the influence of the enabling factors in this process.
<number>
RAC
Final
Report

## Slide 39: To know more about RAC
- Capacity4Dev dedicated page:
http://capacity4dev.ec.europa.eu/public-cd-tc/minisite/rac
- Video interview with the EUD in Bolivia:
http://capacity4dev.ec.europa.eu/public-cd-tc/blog/RAC