## Slide 1: OPSYS WORKSHOP WITH EU DELEGATIONS AND HQ PRACTITIONERS 10-12 October 2016
Focus on results management: presentation of the existing situation
"How EU delegation monitors and follows up on implementation/results with the support of IT tools"
Presentation by Delegation to Bosnia and Herzegovina

## Slide 2: Portfolio of Delegation to Bosnia and Herzegovina
-342 ongoing contracts – 306 in direct management, 36 in indirect management;
- total value of ongoing contracts: €349,839,224 (€211,636,431 direct management and €138,202,793 indirect management).

## Slide 3: Use of various IT tools at different levels of project cycle:
Financing Decisions:
  CRIS reports on decisions with RAC, RAL and deadlines as an internal follow-up tool;
  Some MIS reports also used for certain aspects of execution at the level of decisions.

## Slide 4: Decisions data exported from CRIS with certain info added (for internal follow-up purposes):

## Slide 5: Procurement level – follow-up of the procurement process against the contracting plan:
o MIS reports on the contracting forecast (in the Consolidated MIS Report)
o locally developed detailed report on procurement steps based on MIS data (equivalent MIS report is prepared but not yet deployed).

## Slide 6: MIS structure allows clear definition of procurements steps and its timing:

## Slide 7: Contract signature date is reflected in the "Consolidated report", (current situation):

## Slide 8: The same procurement was planned for contracting in May 2016 (BIP February 2016 contracting forecast)

## Slide 9
Unfortunately there is no comparative report current procurement plan vs. initial plan, therefore identification of projects that are slipping from the original plan requires separate (manual) analysis. However, the comparative report being developed by MIS team, pending its deployment.
An example of the comparative report for follow up of all procurement step, (with possibility to choose per project/procurement phase; herby shown one procurement) follows:

## Slide 11: In the absence of comparative report, locally developed report is in use:

## Slide 12: Contracts - Objectives and achievements at the level of contracts:
MIS Implementation Review reports – individual report for each contract (not allowing overview per sectors, programmes, years etc., as narrative descriptions and not quantifiable data are entered in text fields).

## Slide 13: Based on entries/assessment in MIS:

## Slide 16
MIS data summarised in the Implementation report used for Implementation Reviews
Example follows:

## Slide 19: Risks associated with achievements of results - MIS Risk Assessment – identification and follow-up on risks, additional control plans and execution of planned controls:
o MIS Risk Assessment Report (in the Consolidated MIS Report) – at the level of contracts and procurements – enabling overview of risks and controls for all contracts / procurements (still cannot be sorted by sectors etc.).

## Slide 21: Follow-up on financial execution of contracts – payments and recoveries:
  MIS BIP Fund Management report (in the Consolidated MIS Report);
  Exports of data from ABAC (inappropriate for reporting and follow-up purposes, before CRIS Data Warehouse was used).

## Slide 23: KPIs – EAMR and KPI Dashboard
KPIs as quantifiable indicators which are also used as a follow-up tool on results achieved in a reporting period.
The latest EAMR as an example.

## Slide 24: EAMR – KPI Summary - extract
KPI 1 | Accuracy of initial annual financial forecast for payments | 107.50% |  | Between 90% and 110%
KPI 2 | Accuracy of initial annual financial forecast for contracts | 94.60% |  | Between 90% and 110%
KPI 4 | RAL Absorption Period | 2.88 |  | Not more than 4 years
KPI 7 | Reduction of Old Pre-financing | 51.30% |  | Decrease by 25% at least
KPI 8 | Expired Contracts as a % of the contract portfolio | 10.50% |  | Not more than 15%
KPI 9 | Reduction of Old RAL | 37.30% |  | Decrease by 25% at least

## Slide 25
KPI 14 | Planning and Risk Management Processes | 100.00% |  | At least 80%
KPI 15 | Operations and Control Activities | 98.48% |  | At least 80%
KPI 16 | Information and Finances | 100.00% |  | At least 80%
KPI 17 | Evaluation and Audit | 100.00% |  | At least 80%