## Sheet1
1 - Focus on Operations and Country Level
Status | Action | In charge | Deadline
| 1.1. Mainstream BB principles in the cycle of operations | Delegations/ Centralized Operations Units | ongoing
| 1.2. Boost overall BB implementation at country level/ Geo roadmaps | Delegations | 15/11/2009 + ongoing
| 1.3. Support delegations/country work | Geographical Directorates | ongoing
2 - Quality Assurance at design phase: the QSG
Status | Action | In charge | Deadline
| a) Include a TC focus within the training for all EuropeAid staff on the new QSG system (harmonized assessment ) | E5/CT | 2010-02-28
| b) Ensure active follow up and promote corrective measures | Del/Geo Directors | ongoing
3- Communication, Knowledge Management and Dialogue
Status | Action | In charge | Deadline
3.1 Continue in-house communication
| a. Organize dedicated sessions for Dir A, Dir B and Dir F | Geo Dir. with CT | 2009-12-01
| b. Offer ad hoc presentations/working sessions to operational services and delegations | CT + Geo Dir. | ongoing
| c. Produce a multimedia presentation on Guidelines on TC | E5 | 2009-12-30
| d. Hold presentations addressing Delegation staff and Partner countries when on mission- | Geo Staff /E staff | ongoing
3.2 Broaden up communication to external stakeholders
| a) Organize an event for Civily Society Organisation (CSO) and private sector at HQ | CT | 2009-12-30
| b) Organize regularly short presentations at the info point | E5/CT | ongoing
3.3 Address line DGs
| Develop dialogue, hold presentations and disseminate the BB principles and Guidelines | CT with Geo Dir | 2010-03-30
3.4 Knowledge Management " www. Capacity4Dev.eu"
| a) Implement a marketing strategy following official launch | E5/CT | 2009-12-30
| b) Develop a concise strategy for “capacity4dev” | E5 | 2009-11-30
3.5 Collect and disseminate innovative/good practices
| a) Launch a competition for promising TC with a prize to be awarded | CT | 2010-03-30
| b) Put in place a structured approach to collect good cases through QSG, ROM, Geo team leaders | CT | 2009-12-31
3.6 Panel of external stakeholders
| a) Kick off the panel on "Capacity4dev" | E5 | 2009-10-30
3.7 Policy dialogue at international level
| a) Support development of the “joint EU guidance on TC” | 01/ E5 | ongoing
| b) Further develop dialogue with other donors/agencies (including WB, FMI) and explore collaboration/synergies | CT | ongoing
| c) Participate in DAC initiatives | 01/E5 | ongoing
| d) Participate in the CD Alliance activities | Dir E/E5 | ongoing
4 - Training + ad hoc Support to Operations
Status | Action | In charge | Deadline
4.1 Tailored training/coaching at country and regional level
| a) inform Delegations on training offer and plan country sessions | Geo Dir + CT | 2009-11-30
| b) Implement following demand and budget availability | E5 + ADM
4.2 Training /coaching in HQ
| a) Organize 4 sessions a year of basic training | E5 + ADM | ongoing
| b) Offer dedicated coaching sessions | E5 + Geo Dir | ongoing
5 - Tracking & Monitoring TC/PIUs and the BB implementation
Status | Action | In charge | Deadline
5.1 Set up of an Information System
| a) Include in PCM Platform basic info on TC | E5 + consultant | 2010-03-30
| b) Propose further technical developments like integration of annual mapping from 01/2010 | tbd
5.2 Mapping of TC and of PIUs
| a) Launch/ implement a second round "mapping" exercise with the January 2010 EAMR | CT + G1 | 2010-01-31
| b) Analyse data | Geo Dir + 01 | 2010-03-30
| c) Launch an adapted mapping for Centralised operations | Geo Dir with CT | 2010-02-28
5.3 Monitoring
5.3.1 Global Survey via ROM Monitoring
| a)Review results from the ROM reports from July 2008 to February 2009 | E5 + ROM contractor | 2010-03-30
| b) Include selection of higher number of “significant TC" programmes in the next ROM exercise | CT+Geo Dir
| c) Produce regular analysis |  | ongoing
5.3.2 Building "in depth TC Monitoring"
| a) Identify/mobilize funding for the pilot scheme | E5 | 2009-11-15
| b) Adapt the ROM methodology consulting stakeholders | E5/CT | 2009-11-30
| c) Implement the pilot scheme | E5 | during 2010
| d) Process results of pilot scheme | E5/CT | 2011-03-30
| e) Launch extended "in depth monitoring" | E5/CT | first half 2011
5.4 Evaluation
5.4.1 Global Evaluation on TC
| Global evaluation of TC | Unit 03 | mid 2011
5.4.2 Integration of TC in mid term and final evaluations
| Include guidance on evaluation questions in the ToRs | E5/03
| Include TC aspects when choosing projects to be evaluated | E5/CT | end of 2009
| Compile and disseminte conclusions | E5/CT | from 2011
5.5 QSG
| 1) Under the oQSG "conclusion part" of the checklists, introduce a box for "innovative/promising TC programme" | E5
| b) Train Dir E staff/AIDCO cooperation officers | E5 | 2010-02-28
| c) Include the "quality grid" in the PCM platform | E5 | 2010-06-30
| d) Develop a light methodology to analyse the data | E5 | 2010-03-30
| e) Identify good practices, lessons learnt. Dissemination. | E5 | from 2010
6 - Procedures and Other Ations at System Level
Status | Action | In charge | Deadline
6.1 Follow up Work on procedures
| a) Elaborate "light" guidance on mobilisation of public expertise | CT with Geo support | 2010-06-30
| b) Explore suspensive clause issue | Unit G7 | tbd
| c) Follow up database on Framework Contract(FWC). | Unit F4
6.2 Consider Specific Issues and Produce Light Guidance
| TC in fragile situations : guidance | CT/ad hoc WG | 2010-06-30
| TC implemented through Budget Lines: adapt the Mapping exercise | Dir F | 2010-12-31
| The BB and International Organisations: how to promote the use of BB principles | CT + G8 | 2010-03-30
| The “Topping up" debate in compliance with the BB | CT + Geo Dir. | ongoing
Column1
Done
On Track
On Track with Risk of Delay
Delayed
Dir. A Done
Dir. A On Track
Dir. A On Track with Risk of Delay
Dir. A Delayed
Dir. B Done
Dir. B On Track
Dir. B On Track with Risk of Delay
Dir. B Delayed
Dir. C Done
Dir. C On Track
Dir. C On Track with Risk of Delay
Dir. C Delayed
Dir. D Done
Dir. D On Track
Dir. D On Track with Risk of Delay
Dir. D Delayed
Dir. F Done
Dir. F On Track
Dir. F On Track with Risk of Delay
Dir. F Delayed